## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
01a | Course score | Contain degree level, overall grade, grade for each semester, and grades for each courses. Students can view their degree level, GPA, weighted average score, grade ranking, score for each course, and assignment score. | M | 1 | Ensure that degree grade, total grades, grades for each semester, and scores for individual courses can be viewed separately. Ensure that the query function works properly and the page classification is clear. |  | 3.21 | 3.24
02a | Personal Cultivate Program | In this module, students will get customized learning programs based on personal interests and learning history, while recommended courses, resources and activities, such as elective courses that are suitable for them, can help users learn what they are interested in more efficiently. | S | 1 | The learning programs that users get on this page should be personal and selective. Users can view all the courses, resources, and activities provided, and there should be a short introduction to tell the user what these resources are about. Users can set their own filtering criteria, such as subject category, discipline difficulty, etc., to filter the courses, resources and activities they want. |  | 3.24 | 3.28
02b | Study Arrangement | Help users plan their study arrangement, such as listing tasks, readings and assignments that need to be completed, as well as key dates and deadlines, and remind them at a set time. | M | 2 | Ensure that users can edit in place to list the tasks and dates they want to record. Ensure that the user can set the reminder and that the reminder appears in the correct preset way at the correct preset time. The page should be clear for users to get the information they want quickly. |  | 4.2 | 4.4
03a | Course Selection | Within the time limit，students can select and withdraw from optional courses that are on the list. Time conflicts and courses with full places will be blocked from selection. Course selection results will be synced to the course list | W | 4 | Ensure that the system is able to provide students with the appropriate options based on their personal information Ensure that course titles and credits are displayed correctly Courses with conflicting times and full capacity should be blocked from choosing Ensure that selections can be changed within a specified time frame |  | 5.24 | 5.27
03b | Course Schedule Search | The schedule shows the course name, class time, class location and teacher. The schedule for the day will be made available to students by default. Students can enter a time to check the schedule for that time period | M | 1 | Ensure the course schedule is up to date with the latest results Ensure the schedule can be displayed by date Option to view the timetable for different weeks |  | 3.21 | 3.23
04a | Assessment of Teaching | Students can anonymously evaluate the teacher after the lesson has been completed, and the assessment will be based on a number of dimensions such as content, pace and difficulty | C | 4 |  |  | 5.5 | 5.12
04b | Student Forum | Students can communicate about their studies and share learning materials in the student forum, and can also ask questions to the teacher. Questions and answers are open to the public | W | 4 | Ensure that students can initiate queries with teachers Ensure timely notification of replies |  | 5.1 | 5.2
05a | Personal centre | Students can view the positions they have held at school, the honours and awards they have received at school, and their thesis portfolio, which they can easily export for later use. | M | 1 | Ensure that the search function works properly and that page categories are clear and error-free. Ensure that personal information is not retained after account cancellation |  | 3.24 | 4.11
06a | Notification | The software will deliver timely information on conferences and lectures to facilitate students' extra-curricular learning | C | 2 | Ensure that the correct and relevant information is pushed in a timely manner Ensure that event start reminders can be set |  | 3.28 | 4.11